## Sheet1
QA Bug Report-After Merge Part
Defect ID | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Bug Screen Shot | Status | Assing | Fixed Screen Shot | Estimate time | comment
Candidate Part
1 | Design broken | http://3.9.165.195/auth/candidate/notifications-list go this link and then click message button from above right side | Not separate | Must be separate | High | High | Image | already solved | afsana
2 | Can not upload file 2nd time without refresh | http://3.9.165.195/auth/candidate/profile-edit#portfolio first delete the uploaded portfolio and try to upload the same file without refresh the application | must be able to upload same file 2nd time after delete | Can not upload 2nd time | High | low | Image
3 | No data | http://3.9.165.195/auth/candidate/job-selection go to this link and then click job selection and job type | Data must be there | No data there | High | High | Image
4 | No data | http://3.9.165.195/auth/candidate/job-selection go to this link and then click job selection and Company type | Data must be there | No data there | High | High | Image
5 | doesn't work and have no functionality (post an event) | http://3.9.165.195/auth/candidate/posts go to this link click meetspace then click post an event | Must be have work space with requirements | doesn't work and have no functionality | High | Low | Image
6 | cann't save or copy link | http://3.9.165.195/auth/candidate/posts go to this link then create a post and click 3dots then click copy or save option | must be able to save or copy link for a post | cann't save or copy link | High | High | Image
7 | profile image couldn't update in real time in navbar profile | http://3.9.165.195/auth/candidate/profile-edit#personal-info go to this link and update profile image | must be update profile image in real time | profile image couldn't update in real time in navbar profile | High | High | Image
8 | After hit one like button here shows more | http://3.9.165.195/auth/candidate/settings > settings>help> expant plus button then hit like button | must be shown only hit button | After hit one like button here shows more | High | High | Image
9
10
11