## WebView
QA Bug Report-Candidate
Defect ID | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Bug Screen Shot | Status | Fixed Screen Shot | Done by | Esstemate Time | Questions Comments
1 | No phone number in profile | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and find phone number input field | phone number should be there which i given for sign up. | No phone number there | High | High | Image | fixed | image | Tamim | .1 1 hour
2 | while update link the screen flickering | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "on the web" option | Screen will not flickeing while update link | while update link the screen flickering | High | Low | Image | leave |  | tamim
3 | screen flickeing while I cross the link. | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "on the web" option | Screen will not flickeing while I cross the link | screen flickeing while I cross the link. | High | Low | Image | leave |  | tamim
4 | Can't Move on the web features | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "on the web" option | Though there is menu item, it's must be move in while user want | Can't Move on the web features | Low | Low | Image | fixed |  | tamim | 15 min
5 | File name out of it's own area | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "portfolio" option then upload a codument with large name | File name should be on his own area | File name out of it's own area | High | High | Image | fixed | fix pic | Tamim | .03 30 minit
6 | Screen flickering | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "portfolio" option then upload a codument | Screen Won't flickering while upload a document in porfolio | flickering screen while upload a portfolio documents | High | High | Image | fixed | image | tamim | .03 30 minit
7 | Doesn't found unfilled area as input | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "work experience" option then filled some option and click on save button | Should locate the area which is mandator to filled up | Cant locate the area | High | Low | Image | Fixed | image | Tamim | .03 30 minit
8 | skill set save issue | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "skills" option then filled some option and click on save button | Selected issue will shown properly | selected 12 but show only shown 3 | HIgh | `low | Image | Fixed | image | Tamim | .03 30 minit
9 | Arrow sign desing | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "skills" option then filled some option and click on save button | Arrow sign must be separate from numeric number | Now this arrow sign attached with the number | High | Low | Image | Fixed | image | Tamim | .03 30 minit
10 | Error can not redirect | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "certificate" option then filled some option and click on save button | Error message must be redirect where actually error found | error message can not redirect | High | High | Image | fixed | image | Tamim | .03 30 minit
11 | Design problem | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "job interest" option then filled some option and click on save button | save preferences and cancel button is so close with availability input field. it's must be seperate | these button are so close | High | High | Image | fixed | image | Afsana & Tamim | .03 30 minit
12 | Message icon option doesn't work | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "job interest" option then filled some option and click on save button | After clicking message icon it's be working with the right functionality | no functionality for message | High | High | Image |  |  | Afsana | 0.4 5 min | need design
13 | Need to redesign | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "additional information" option then filled some option and click on save button | Need to redesign | Looks awkward | High | Low | Image |  |  | Afsana | 0.4 5 min | need design
14 | Cancel button doesn't working | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down then find "additional information" option then filled some option and click on save button | Cancel must be working properly | cancel button doesn't work | High | High | Image | fixed | image | Tamim | .1 1 hour
15 | Design broken | "http://3.9.165.195/auth/candidate/profile" go to this link and check portfolio document | Design not be broken | Design broken | Low | Low | Image | fixed | image | Tamim | .03 30 minit
16 | Linkedin doesn't work | "http://3.9.165.195/auth/candidate/job-selection/375" go to this link and try to share the job in linkedin | Linkedin icon must be working perfectly | doesn't work | High | hIgh | Image | ismail will look for it | image | Afsana | 0.4 30 -40min | only 3 M.byte website can load here. more
17 | Twitter doesn't work | "http://3.9.165.195/auth/candidate/job-selection/375" go to this link and try to share the job in twitter | twitter icon must be working perfectly | doesn't work | High | HIgh | Image | fixed | image | Afsana | 0.4 35 min
18 | Facebook doesn't work (View Employer Profile) | "http://3.9.165.195/auth/candidate/view-employer-profile/145/371" go to this link and scroll down then find facebook and click on it | Facebook icon must be working perfectly | doesn't work | High | HIgh | Image | solved | image | tamim | .03 30 minit
19 | Linkedin doesn't work (View Employer Profile) | "http://3.9.165.195/auth/candidate/view-employer-profile/145/371" go to this link and scroll down then find linkedin and click on it | Linkedin icon must be working perfectly | doesn't work | High | HIgh | Image | solved | image | tamim | .03 30 minit
20 | Twitter doesn't work (View Employer Profile) | "http://3.9.165.195/auth/candidate/view-employer-profile/145/371" go to this link and scroll down then find twitter and click on it | twitter icon must be working perfectly | doesn't work | High | HIgh | Image | solved | image | tamim | .03 30 minit
21 | See all button must be working (View Employer Profile) | "http://3.9.165.195/auth/candidate/view-employer-profile/145/371" go to this link and click see all button from right side | See all button must be working | doesn't work | High | High | Image | pass to ismail |  | Afsana | 0.4 20 min | route link created but path is not correct
22 | Apply now button should be "applied" | "http://3.9.165.195/auth/candidate/job-selection/371" go this link and click apply now button | Apply now button should be applied. | After apply any job, it shows again apply now though after clicking apply now 2nd time, it's shows error, | Low | Low. | Image | Already fixed | image | Afsana | 10 min
23 | Send referral doesn't work | "http://3.9.165.195/auth/candidate/job-selection/371" go this link and scroll down then click on send refferal. | Send referral must be working | Send referral doesn't work | HIgh | High | Image |  |  | afsana | 0.4 5 min | need requirments-afsana
24 | filter doesn't work for Z-A | "http://3.9.165.195/auth/candidate/job-selection" go to this link and try filter | Filter must be working | doesn't work | HIgh | High | Image | Already fixed | IMAGE | Afsana | 20 min
25 | filter doesn't work for A-Z | "http://3.9.165.195/auth/candidate/job-selection" go to this link and try filter | Filter must be working | doesn't work | HIgh | High | Image | Already fixed | IMAGE | Afsana | 20 min
26 | can't share on linkedin | "http://3.9.165.195/auth/candidate/posts" go to this link and create a post and try to share on linkedin | Must be share i linkedin | If I want to share in linkedin and click on it than it's turn into the twitter. | HIgh | High | Image | fixed | IMAGE | Afsana | 20 min
27 | can't share on twitter | "http://3.9.165.195/auth/candidate/posts" go to this link and create a post and try to share on twitter | Must be share i twitter | If I want to share in twitter and click on it than it's turn into the linkedin. | HIgh | High | Image | fixed | IMAGE | Afsana | 20 min
28 | personal design button have no work or function | "http://3.9.165.195/auth/candidate/posts" go to this link and click on premium memberhsip then personal design | Personal design button will have work | personal design button have no work or function | HIgh | High | Image |  |  | afsana | 0.4 5 min | Need requirments contents -afsana
29 | lottery button has no work or functionality | "http://3.9.165.195/auth/candidate/posts" go to this link and click on premium memberhsip then lottery | Lottery button will have work | lottery button has no work or functionality | HIgh | High | Image |  |  | afsana | 0.4 5 min | Need requirments contents -afsana
30 | post an event button doesn't work | "http://3.9.165.195/auth/candidate/posts" try to post an event | post an event button must be working | post an event button doesn't work | HIgh | High | Image |  |  | afsana | 0.4 5 min | Need requirments contents -afsana
31 | save button doesn't work | "http://3.9.165.195/auth/candidate/posts" go to this link and try to save a post. | post must ba saved | post can not saved after cliking | HIgh | High | Image |  |  | afsana | 0.4 5 min | Need requirments contents -afsana
32 | copy link to post doesn't work | "http://3.9.165.195/auth/candidate/posts" try to copy any post link | copy link must be copy | can't copy any post link | HIgh | High | Image | Already fixed | IMAGE | Afsana | 30 min
33 | Doesn't recognized a valid email address. | "http://3.9.165.195/auth/candidate/support-ticket" go to this link and create ticket with invalid email address. | Must be taken a valid address | I did not submit a valid email but it's taken invalid email address | HIgh | High | Image | Fixed | image | Tamim | .03 30 minit
34 | Created ticket deleted issue | "http://3.9.165.195/auth/candidate/support-ticket" go to this link and create ticket then click 3 dots and then click discard | discard button will be delete button if the discard button function is delete. | After clicking discard then created ticket deleted | Low | Low | Image | Already fixed | IMAGE | Afsana | 15 min
36 | Design broken in ipnonex | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and scroll down | Design not be broken | Design broken | High | High | Image | fixed | IMAGE | Afsana | 30 min
37 | Arrow sign issue | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select industry drop down data more than 3 | Arrow sign must be separate | Arrow sing combine with selected portion | High | Low | Image | fixed | image | Tamim | .03 30-40 minit
38 | Arrow sign not visible | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select skilled drop down data more than 4 | Arrow sign must be separate | Arrow sing combine with selected portion | High | Low | Image | fixed | image | Tamim | .03 30-40 minit
39 | Design broken in education industry | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select industry drop down data more than 3 from education edit option | Design not be broken | Design broken in education industry | High | Low | Image | fixed | image | tamim | .03 30 minit
40 | Design broken in education start year | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select education then click start year | Design not be broken | Design broken in education start year | High | Low | Image | already ixed | IMAGE | Afsana | 15 min
41 | Design broken in education end year | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select education end year | Design not be broken | Design broken | High | Low | Image | already ixed | IMAGE | Afsana | 10 min
42 | Save and canecl button must be separate | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and then create education then try to edit it and see save and cancel button attatched below. | Save and canecl button must be separate | Design broken in education end year | Low | low | Image | fixed | IMAGE | Afsana | 10 min
43 | Arrow sign not visible | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select certificate industry drop down data more than 3 | Arrow sign must be separate | Arrow sign not visible | High | low | Image | fixed | image | Afsana | 20-40 min
44 | Design broken in languages edit profile | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select language more than 3 | Design not be broken | Design broken in languages edit profile | High | High | Image | fixed | image | Afsana | 10-15 min
45 | Design broken in job interest region selection | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select region selection under job interest | Design not be broken | Design broken in job interest region selection | High | High | Image | fixed | image | Afsana | 25 min
46 | Design broken in job interest industry selection | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select industry under job interest | Design not be broken | Design broken in job interest industry | High | High | Image | already fixed | image | afsana
47 | Arrow sign visible partically under select job type in job interest | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select job type under job interest | arro sing must visible fully | Arrow sign visible partically | High | low | Image |  |  | Afsana | 5 min | need to review
48 | Design broken in availabilty in job interest | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and availabality under job interest | Design not be broken | Design broken | High | High | Image | fixed | IMAGE | Afsana + Tamim | .03 30-40 minit
49 | Check desing in payment information | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and check attached image | Suggestion | Suggestion | High | low | Image | fixed | IMAGE | Afsana | 15-25min
50 | Check desing in payment information "Handicap and save button fixed" | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and check attached image for handicape information | Suggestion | Suggestion | High | High | Image | fixed | image | AFsana+Tamim | .03 30-40 minit
51 | Check desing in additional information | "http://3.9.165.195/auth/candidate/profile-edit" go to this link and select soft skills under additional information | Design not be broken | Design broken | High | High | Image. | fixed | image | Tamim | .03 30 minit
52 | can not accept contact request | http://3.9.165.195/auth/candidate/my-jobs go to link and check job offers then click accept | Should be accept contact request | can not accept contact request | High | High | Image |  |  | Tamim | 0.4 5 min | need to store in database no code given
53 | this portion must have distance | http://3.9.165.195/auth/candidate/dashboard go to this link for dashboard and check | this portion must have distance | there is no distance between them (check image | High | High | Image | not exist | image | afsana
54 | Details button should be it's own area | http://3.9.165.195/auth/candidate/dashboard go to this link for dashboard and scroll down | Details button should be it's own area | Details button out of it's area | low | Low | Image | fixed | image | Afsana | 0.4 30-35 min
55 | design broken | http://3.9.165.195/auth/candidate/job-alert go to this link and create job alert with large name | design should not be broken | design broken | high | high | Image | fixed | image | tamim | .03 30-40 minit
56 | Logo must be separate | http://3.9.165.195/auth/candidate/view-employer-profile/145/351 go to this link and scroll down | Logo must be separate | now logo is togather | low | high | Image | fixed | image | tamim | .03 30 minit
57 | See all button doesn't work | http://3.9.165.195/auth/candidate/view-employer-profile/145/351 go to this link and scroll down then click see all button | see all button must be work | See all button doesn't work | High | high | Image |  |  | Tamim | 0.4 5 min | no routes created button was desabled
58 | design broken | http://3.9.165.195/auth/candidate/job-selection/365 go to this link and check (attached image) | design should not be broken | design broken | High | High | Image | fixed | image | tamim | 0.03 30 minit
59 | nave bar but be close after clicking dropdown option | http://3.9.165.195/auth/candidate/job-selectio go to this link and click navbar then select any dropdown option | nave bar but be close after clicking dropdown option | dropdown menu open with navbar | High | High | Image | fixed | image | tamim & afsana | 1 day
60 | need to redesign | http://3.9.165.195/auth/candidate/posts and check attached image | need to redesign | need to redesign | High | High | image | fixed | image | Tamim | .03 30-40 minit
61 | after clicking apply then show blank | http://3.9.165.195/auth/candidate/my-job go to this link and click my job then click apply button one of the jobs | after open a modal all details will be there | after clicking apply then show blank | High | High | Image | (now don't work on that bug ok )
62 | got message from employee but if i click on message it's doesn't work | http://3.9.165.195/auth/candidate/notifications-list go to this link and click on message option then message | after clicking on message it's must be shown for the candidate | got message from employee but if i click on message it's doesn't work | High | High | Image |  |  | Tamim |  | onChatClick() function not created
63 | Delete button doesn't work | http://3.9.165.195/auth/candidate/notifications-list go to this link and click on message option then message 3 dots then take action on button showed | Delete button must be work properly | Delete button doesn't work | High | High | Image |  |  | Tamim |  | no route for delete and not functionality created
64 | bugExtra | [5 empty] | image | fixed | image | afsana | 1 h
65 | bugExtra | [5 empty] | image | fixed | image | afsana | 45min
66 | bugExtra | [5 empty] | image | fixed | image | afsana | 30-40 min
67