## Sheet1
QA Bug Report-Employee Part
Defect ID | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Bug Screen Shot | Status | Assing | Fixed Screen Shot | Estimate time | comment
1 | Refferal link doesn't work | http://3.9.165.195/auth/employer/profile go to this link and click refferal link | link must be work | Link doesn't work | High | High | Image | already fixed | afsana |  | 10 min
2 | Cross button linked togather | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and select industry from dropdown menu | "X" cross button should separate | "X" cross option linked togather with the selected portion | High | High | Image | fixed | tamim | image | .03 30 minits
3 | Error message cant redirect where is error actualy | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and complete the general infromation without one of them and click save button | Must be redirect where is shown error | Error message cant redirect where is error actualy | High | High | Image | already fixed | tamim | image | .03 30 minits
4 | Taken as invalid phone number | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and complete the general infromation with invalid phone number and click save button | Should taken valid number | Taken invalid phone number | High | High | Image | pass to ismail | tamim | image | .03 30 minits | country code not given- ismail will fix it
5 | Screen flickering after give a social media link | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and give social media or other link on that portion "on the web" | Screen should not flickering | Screen flickering after give a social media link | High | High | Image | leave
6 | Save button doesn't work | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and give value then click save button | save button must be work | Save button doesn't work | High | High | Image | already fixed | tamim | image | .03 30 minits
7 | In benefit section has no data (need to discuss) | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and the go to benefits of option then click "+" plus button | In benefit section has no data (need to discuss) | In benefit section has no data (need to discuss) | High | High | Image | already fixed | tamim
8 | can't upload any photo in gallary section | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and then click gallary option and upload a photo | photo must be taken as upload | can't upload any photo in gallary section | High | High | Image | need database requirments | afsana |  | 2h
9 | After update name for employee it's doesn't update in real time | http://3.9.165.195/auth/employer/edit-profile go to this link and change the existing name of company then click save button | Name must be updated with real time view | doesn't update with real time | High | High | Image | already fixed | tamim | image | .03 30 minits
10 | "X" button must be separate | http://3.9.165.195/auth/employer/post-job go to this link and select job industry | "X" button must be separate | Now "X" cross but is so close with selected part | High | High | Image | fixed | tamim | image | .03 30 minits
11 | "X" button must be separate | http://3.9.165.195/auth/employer/post-job go to this link and select region and job type | "X" button must be separate | Now "X" cross but is so close with selected part | High | High | Image | fixed | tamim | image | .03 30 minits
12 | "X" button must be separate | http://3.9.165.195/auth/employer/post-job go to this link and select soft skills | "X" button must be separate | Now "X" cross but is so close with selected part | High | High | Image | fixed | tamim | image | .03 30 minits
13 | soft skill drop down must be above | http://3.9.165.195/auth/employer/post-job go to this link and click soft skills option | soft skill drop down must be above | Now it's below and not user friendly | High | High | Image | fixed | tamim | image | .03 30 minits
14 | no selectable template here (need to discuss with developer and owner) | http://3.9.165.195/auth/employer/edit-job/edit/4/426/preview go to this link and click on select template | need to discuss | No templete here to select | High | High | Image | need document |  |  |  | need document
15 | Screen flickering after click save button | http://3.9.165.195/auth/employer/edit-job/edit/4/426/preview go to this link and click on save | screen will not be flickering | Screen flickering after click save button | High | High | Image | already solved | Afsana | image | 10-25 min
16 | Can not share any job in social media | http://3.9.165.195/auth/employer/edit-job/edit/4/426/preview-publish?paymentId=4 then try to share this job on linkedin+facebook+ twitter | must be able to share this job in social media | Can not share any job in social media | High | High | Image | fixed | Afsana+tamim | image | 30-40 min | for linked in- real link needed
17 | Can not share any job in social media (below part ) | http://3.9.165.195/auth/employer/edit-job/edit/4/426/preview-publish?paymentId=4 then try to share this job on linkedin+facebook+ twitter | must be able to share this job in social media | Can not share any job in social media | High | High | Image | fixed | tamim | image | .1 1 hour
18 | showed 2 delete and edit icon for different template | http://3.9.165.195/auth/employer/accept-reject-manager go to this link and click from 2 different 3dot option to edit | Only one modal will open at a time | showed 2 delete and edit icon for different template | High | High | Image | fixed | tamim | image | 2 2 days
19 | I did not upload any document but it shows document uploaded successfully | http://3.9.165.195/auth/employer/hiring-manager go to this link and click save button | without any document should not be saved. | I did not upload any document but it shows document uploaded successfully | High | High | Image | need to discuss with ismail
20 | Must be able to download portfolio (file) | http://3.9.165.195/auth/employer/candidate-profile/170 go to this link and download candidate portfolio | Must be able to download portfolio (file) | Cant download | High | High | Image | fixed | tamim & afsana | image | 1 1 day
21 | after creating a post screen turn into blue | http://3.9.165.195/auth/employer/posts go to this link and create a post | screen should not be blur | after creating a post screen turn into blue | High | High | Image | Already fixed | tamim & afsana
22 | if I click on linkedin to share it's turn into twitter | http://3.9.165.195/auth/employer/edit-profile#general-info go to this link and give value then click save button | must be able to share only linkedin if i click on linkedin | if I click on linkedin to share it's turn into twitter | High | High | Image | fixed | Afsana | image | 15 min
23 | if I click on twitter to share it's turn into linkedin | http://3.9.165.195/auth/employer/posts go to this link and create a post then click on share and click twitter icon | must be able to share only twitter if i click on twitter | if I click on twitter to share it's turn into linkedin | High | High | Image | fixed | Afsana | image | 5 min
24 | No user name shown after creating a post | http://3.9.165.195/auth/employer/posts go to this link and create a post then check user name | User name must be shown | No user name shown after creating a post | High | High | Image | fixed | tamim | image | 1 1 day
25 | Can't save any post | http://3.9.165.195/auth/employer/posts go to this link and create a post then click 3 dots from right side then click save option | Post must be saved | Can't save any post | High | High | Image | need requirments | Afsana |  |  | need requirments
26 | Can't copy link of created post | http://3.9.165.195/auth/employer/posts go to this link and create a post then click 3 dots from right side then click copy link | must be able to copy link for created post | Can't copy link of created post | High | High | Image | already fixed | Afsana | image | 0.4 5 min
27 | Screen flickering after click like button | http://3.9.165.195/auth/employer/posts go to this link and create a post then click like button | screen should not be flickering | Screen flickering after click like button | High | High | Image | leave
28 | Social media button color should light / it's own color | http://3.9.165.195/auth/employer/posts go to this link and create a post then click share button then check | Social media button color should light / it's own color | Now these buttons color is deep | High | High | Image | need to reiew | Afsana |  |  | need to reiew
29 | No option to edit my post | http://3.9.165.195/auth/employer/posts go to this link and create a post then click 3dots option and check edit option | Must contain there edit option | No option to edit my post | High | High | Image | need requirments | Afsana |  |  | need requirments
30 | Need to compress the large image size | http://3.9.165.195/auth/employer/posts go to this link and create a post with large image (height and width) | Need to compress the large image size | now it's look like boaring | High | High | Image | fixed | Afsana | image | 20-40 min
31 | Post an event button doesn't work | http://3.9.165.195/auth/employer/posts go to this link and click post an event | Post an event button must be work | Post an event button doesn't work | High | High | Image | need requirments | Afsana |  |  | need requirments
32 | Screen flickering | http://3.9.165.195/auth/employer/settings go to this link and click help and then click "+' button then hit like button | Screen should not flickering | Screen flickering | High | High | Image | leave
34 | need enough space | http://3.9.165.195/auth/employer/post-job go to this link> create a job > then check it (attacked image to specify) | need enough space | No enough space (check attacked image) | High | High | Image | already fixed | Afsana | image | 5-10 min
35 | Shown error message | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message | No way to show error message | just shown error without any action | High | High | Image | already fixed | Afsana | image | 5-10 miin
36 | send invite functionality doesn't work | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message then click invite button | Send invite functionality must be work properly | send invite functionality doesn't work | High | High | Image | need requirments | Afsana |  | 1h
37 | Screen flickering | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message | Screen should not be flickiering | screen flickering after enter this page via message option | High | High | Image | leave
38 | show error after clicking send button with text. | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message then click send button with some text. | Error message should not be shown | show error after clicking send button with text. | High | High | Image | Already fixed | Afsana | image | 10-20min
39 | message taken only half space | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message then click send button with some text. | It might be better if text taken full space | message taken only half space | Low | Low | Image | already fixed | Afsana
40 | "*" star button doesn't work | http://3.9.165.195/auth/employer/chat?roomId=187-170 go to this link and click message option for cadidate message then put the mouse cursor on the cadidate 3 dots option. | Star button must be work | "*" star button doesn't work | High | High | Image | already fixed | tamim | image | .03 30 minits
41 | Can't boost job | http://3.9.165.195/auth/employer/job-list/432/candidate-search go to this link and click boost job | Must be able to bost job | Can't boost job and shown an error | High | High | Image | pass to ismail
42 | Feed doesn't open | http://3.9.165.195/auth/employer/dashboard go to link and click open feed from right side | Feed must open | Feed doesn't open | High | High | Image | route file is not created yet | Afsana |  |  | route file is not created yet
43 | hover effect should reduce | http://3.9.165.195/auth/employer/dashboard go to link and click today then put mouse cursor on upcoming | hover effect should reduce | not separate hover effect | Low | Low | Image | fixed | Afsana | image | 15-20min
44 | shown error after clicking on messages | http://3.9.165.195/auth/employer/dashboard go to link and click today then click on messages | Error message should not be shown | shown error after clicking on messages | High | High | Image | already solved | Afsana | image | 10-15 min
45 | can not produce button which maintain in webview | http://3.9.165.195/auth/employer/dashboard go to this link and put cursor of the message 3dots | these button must be there | can not produce button which maintain in webview | High | Low | Image | need details | Afsana |  |  | need details
46 | Design broken in mobile devices | http://3.9.165.195/auth/employer/job-list go to this link and check | Design should not be broken | Design broken | High | High | Image | fixed | Afsana | image | 20-25 min
47 | drop down menu should separate | http://3.9.165.195/auth/employer/job-list go to this link and select job industry | drop down menu should separate | now dropdown menu and 'x' sign are togather | High | High | Image | fixed | tamim | image | .03 30 minits
48 | Work load sticky should visible fully | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then check | Work load sticky should visible fully | Work load visible but particially | High | High | Image | fixed | tamim | image | .03 30 minits
49 | Design broken in mobile devices | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then find language and click on that | Design should not be broken | Design broken | High | High | Image | fixed | tamim | image | .1 1 hour
50 | selected languages must be on the table area | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then find language and click on that and select more than 3/4 languages | selected languages must be on the table area | Selected languages out of its area | High | High | Image | fixed | tamim | image | .03 30 minits
51 | selected EDV Skill be on the table area | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then select EDV Skill more than 3/2 | selected edv skill must be on the table area | Selected edv skills out of its area | High | High | Image | fixed | tamim | image | .03 30 minits
52 | drop down menu should separate | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then select EDV Skill more than 3/3 and then check drop down option | drop down menu should separate | Drop down option not separate now | High | High | Image | fixed | tamim | image | .03 30 minits
53 | arrow and cross "x" button should separate | http://3.9.165.195/auth/employer/job-list go to this link and scroll down then select soft Skill more than 3/3 and then check arrow and cross button | arrow and cross "x" button should separate | arrow and cross "x" button not separate | High | High | Image | fixed | tamim | image | .03 30 minits
54 | Design broken | http://3.9.165.195/auth/employer/edit-job/edit/4/434/preview and then check your plans | Design should not be broken | Design broken | High | High | Image | fixed | Afsana | image | 30-40 min
55 | design broken | http://3.9.165.195/auth/employer/job-list/434/candidate-search go to this link and check publish jobs | Design should not be broken | design broken | High | High | Image | fixed | Afsana | image | 30-40 min
56 | Need some space | http://3.9.165.195/auth/employer/job-list go to this link and scroll down | Need some space | No space there | Low | Low | Image | fixed | Afsana | image | 35-45 min
57 | Delete button doesn't work in accept/reject portion | http://3.9.165.195/auth/employer/accept-reject-manager go to this link click on of the 3dots option then click delete button | Though there is delete button so it's must be working properly | Delete button doesn't work in accept/reject portion | High | Low | Image | leave to ismail
58 | might be better if there is some gap between | http://3.9.165.195/auth/employer/accept-reject-manager go to this link and check with attached image | might be better if there is some gap between | There is no gap | High | Low | Image | fixed | Afsana | image | 30-40 min
59 | Large Name document break in hiring page | http://3.9.165.195/auth/employer/hiring-manager and upload a large name documents | large name should not break | break the area | High | High | Image | fixed | Afsana | image | 30-40 min
60 | Would be better if the document is middle | http://3.9.165.195/auth/employer/hiring-manager and upload a documents | Would be better if the document is middle | Not middle | Low | Low | Image | fixed | Afsana | image | 20-35 min
61 | Arrow button need to be visible clearly in navbar | http://3.9.165.195/auth/employer/ go to this link and click on navbar | Arrow button need to be visible clearly | Not clear fully | High | High | Image | need to talk with ismail | Afsana |  |  | need to talk with ismail
62 | file name must be behind of the navbar | http://3.9.165.195/auth/employer/hiring-manager and upload a documents then click on navbar | file name must be behind of the navbar | file name above of the navbar | High | High | Image | fixed | Afsana | image | 20-35 min
63 | document name must be behind of the message modal | http://3.9.165.195/auth/employer/hiring-manager and upload a documents then click on message icon | document name must be behind of the message modal | file name above of the message modal | High | High | Image | fixed | Afsana
64 | document name must be behind of the notification modal | http://3.9.165.195/auth/employer/hiring-manager and upload a documents then click on notification icon | document name must be behind of the notification modal | file name above of the notification modal | High | High | Image | fixed | Afsana
65 | modals are not same | http://3.9.165.195/auth/employer and click on message icon and notification icon | notification and message modal must be same | notification and message modal are not same | High | High | Image | fixed | Afsana | image | 30-40 min
66 | can not select date for make a meeting in mobile | http://3.9.165.195/auth/employer/chat?roomId=187-168 go this link or click talentpol> click message>click meeting icon | must be able to make a meeting | can not select date for make a meeting | High | High | Image | fixed | tamim | you have to tap and hold any date in mobile | .03 30 minits
67 | Design break | http://3.9.165.195/auth/employer/posts click meet space and click share icon | Design should not be broken | Design broken | High | High | Image | fixed | Afsana | image | 30-45 miin
68 | If I want to post a image without text then shown error but also close the post modal which is should not be | http://3.9.165.195/auth/employer/posts click meet space and select a photo then click post button | If I want to post a image without text then shown error but also close the post modal which is should not be | close the post modal and shown error | High | High | Image | fixed | tamim | image | .1 1 hour
69 | image shown in a small size though there is a a space | http://3.9.165.195/auth/employer/posts click meet space and try to post then check image | image shown in a small size though there is a a space | Image shown in a small size | High | High | Image | fixed | Afsana | image | 30-45 miin
70 | need some gap for 'X' button | http://3.9.165.195/auth/employer/posts go to this link and click navbar then click title menu option | need some gap for 'X' button | no gap between 'x' cross button and title | High | High | Image | fixed | Afsana | image | 30-40 min
71 | there is no name shown of the post owner | http://3.9.165.195/auth/employer/posts go this link and create a post and then check the name of the owner | Post owner name must be there | there is no name shown of the post owner | High | High | Image | pass to ismail | tamim
72 | It would be better, if the navbar is close after clicking the one of navbar feartures | http://3.9.165.195/auth/employer/posts go this link and click navbar then click one of the feautres | It would be better, if the navbar is close after clicking the one of navbar feartures | Navbar not close at present | High | High | Image | fixed | tamim | image | .2 2 hours
73 | Need gap | http://3.9.165.195/auth/employer/settings then click settings>subcription then check with image | Need gap | No gap there | Low | Low | Image | fixed | Afsana | image | 30-40 min
74 | after hit the like/dislike button it's turn into the first one. | http://3.9.165.195/auth/employer/settings>click help > scroll down and expand one of them>hit like button | "after hit the like/dislike button it's should not turn into the first one or other space. It must be there | after hit the like/dislike button it's turn into the first one. | High | High | Image | already fixed | tamim | image
75 | Need gap there | http://3.9.165.195/auth/employer/settings>click help > scroll down and check with attached image | Need gap there | No gap there | Low | Low | Image | fixed | tamim | image | .03 30 minits